## Action Plan
Phase | Task | Output | Owner | Due (date) | Status | Notes
0. Setup | Define ICP + segments + regions (EU + LATAM); pick 2–3 offers | 1-page ICP + offers | You |  | Not started
0. Setup | Create target list (200 accounts) by segment; prioritize Top 50 | Target list v1 | You/Assistant |  | Not started
1. Data | Enrich each account with 1–2 decision-maker roles + LinkedIn URLs | Lead enrichment | You/Assistant |  | Not started
1. Data | Find best contact email (public/company) where possible; otherwise LinkedIn only | Email/LinkedIn ready | You |  | Not started
2. Messaging | Finalize 6 segment templates + 2 follow-ups each (LinkedIn + email) | Template pack | Assistant |  | Not started
2. Messaging | Write 50 ultra-personalized openers (1 sentence each) for Top 50 | Hook lines | You/Assistant |  | Not started
3. Send | Week 1: Send 10/day (Mon–Fri) to Top 50 (mix email + LinkedIn) | 50 outreaches sent | You |  | Not started
3. Send | Week 2: Send next 50 + follow up on non-responders from Week 1 | 100 outreaches sent | You |  | Not started
4. Follow-up | Follow-up #1 at +5 business days; #2 at +10 business days | Follow-up cadence | You |  | Not started
5. Improve | Weekly review: response rate, meetings booked, best hooks; iterate templates | Weekly optimizations | You/Assistant |  | Not started

## OUTREACH LIST INVESTORS
Segment | Sub-segment | Organization | Region | Strategic Rationale / Why Now
Investor | Climate / Infrastructure VC | 2150 VC | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | AENU | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | SET Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | ETF Partners | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | World Fund | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Planet A Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Revent | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Demeter | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Partech Climate | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Energy Impact Partners | EU/US | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Extantia Capital | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Speedinvest Climate | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Project A | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Norrsken VC | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Balderton Climate | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Seaya Andromeda | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Blume Equity | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Contrarian Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Clean Energy Ventures | EU/US | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Galvanize Climate Solutions | Global | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Breakthrough Energy Ventures Europe | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Inven Capital | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Ananda Impact Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | LGT Lightstone | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | KOMPAS VC | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Blue Bear Capital | EU/US | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Alpana Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Circularity Capital | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | Eurazeo Planetary Boundaries | EU | Active climate/infra investment; early de-risking critical
Investor | Climate / Infrastructure VC | 2050 Ventures | EU | Active climate/infra investment; early de-risking critical
Investor | Energy Transition & Impact Fund | Breakthrough Energy Ventures | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Just Climate | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Lowercarbon Capital | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Mirova | EU/LATAM | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | BlueOrchard | LATAM | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | ResponsAbility | LATAM | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | ACCIONA Impact | EU/LATAM | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Energy Transition Ventures | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | LeapFrog Climate | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Carbon Equity | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | IFU | LATAM | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | TPG Rise Climate | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Brookfield Global Transition | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Macquarie Green Investments | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Actis Energy | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Copenhagen Infrastructure Partners | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Arjun Infrastructure Partners | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Greencoat Capital | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | I Squared Climate | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | InfraRed Capital | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Eiffel Investment Group | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Quinbrook Infrastructure | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | KKR Global Climate | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Generate Capital | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Vision Ridge Partners | Global | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Mercuria Energy Transition | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Lightsource bp Ventures | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Aquila Clean Energy | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Octopus Energy Generation | EU | Deploying large-scale transition capital under time pressure
Investor | Energy Transition & Impact Fund | Stonepeak Energy Transition | Global | Deploying large-scale transition capital under time pressure
Investor | Development Bank / Public Finance | European Investment Bank (EIB) | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | EBRD | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | KfW | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | FMO | Global/LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | IDB Invest | LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | CAF | LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | World Bank Energy Practice | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | IFC | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Green Climate Fund (GCF) | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Nordic Investment Bank (NIB) | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Asian Development Bank (ADB) | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | African Development Bank (AfDB) | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | French Development Agency (AFD) | EU/LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | JICA | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | UK Export Finance (UKEF) | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | CDP | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Dutch RVO | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Proparco | EU/LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Finnfund | EU/LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Sida | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | Norad | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | SECO | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | KfW DEG | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | EIB Global | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | IDB Lab | LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | CAF Invest | LATAM | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | OECD Development Centre | EU | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | UNDP Energy | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | GEF | Global | Public capital driving geothermal & energy security mandates
Investor | Development Bank / Public Finance | IRENA | Global | Public capital driving geothermal & energy security mandates

## OUTREACH LIST Developers
Segment | Sub-segment | Organization | Region | Strategic Rationale / Why Now
Developer | Geothermal Developer | EnBW Geothermal | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Eavor | EU/Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Baseload Capital | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Eavor Technologies | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | GeoThermal Engineering GmbH | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Daldrup & Söhne | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Exorka | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | GNS Gesellschaft für Nuklear-Service | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Geoenergie Suisse | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Innargi | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Vulcan Energy Resources | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | E.ON Geothermal | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Ormat Technologies | EU/Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Cyrq Energy | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Heliogen Geothermal | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Magenta Geothermal | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Calpine Geothermal | Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Energy Development Corp (EDC) | LATAM | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | ENGIE Geothermal | EU/LATAM | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Star Energy | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Chevron New Energies (Geothermal) | Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Pertamina Geothermal | Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | AltaRock Energy | Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Dandelion Energy | EU/US | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | GTherm | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | E2E Energy Solutions | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | GeoGlobal Energy | LATAM | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | Taqa Geothermal | Global | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | DEEP Earth Energy | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Geothermal Developer | GreenFire Energy | EU | Scaling geothermal under heat-transition and energy-security pressure
Developer | Renewable IPP / Utility | Ørsted | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | RWE Renewables | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Iberdrola Renovables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | EDP Renewables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | ENGIE Renewables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Statkraft | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Vattenfall | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | ACCIONA Energía | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | TotalEnergies Renewables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Enel Green Power | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Lightsource bp | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | BayWa r.e. | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | RES Group | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Mainstream Renewable Power | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Voltalia | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Neoen | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Akuo Energy | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Q ENERGY | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Encavis | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Octopus Energy Generation | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Aquila Clean Energy | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Green Investment Group | EU | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Masdar Clean Energy | Global | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Brookfield Renewable | Global | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Scatec | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Atlas Renewable Energy | LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | AES Andes | LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Celsia | LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Grenergy Renovables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Renewable IPP / Utility | Naturgy Renewables | EU/LATAM | Rapid site screening needed to accelerate project pipelines
Developer | Land / Project Developer | BayWa Energy Solutions | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Triodos Project Finance | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | WPD | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Low Carbon | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Element Power | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | InfraVia Renewables | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Downing Renewables | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | GIG Energy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | TagEnergy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Eurus Energy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Enerparc | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Lightsource Projects | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | RES Projects | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Windvision | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Sunrock | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Greenalia | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Photon Energy | EU/LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Atlas Agro | LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Zelestra | LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Atlas Renewable (Projects) | LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Grupo Cobra | LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Cox Energy | LATAM | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Contigo Energía | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | BlueFloat Energy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Simply Blue Energy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Ocean Winds | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Renantis | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Qualitas Energy | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Everoze | EU | Land-use optimisation and early feasibility decisive for project value
Developer | Land / Project Developer | Terra Firma Energy | EU | Land-use optimisation and early feasibility decisive for project value

## Outreach List Government & Publ
Segment | Sub-segment | Organization | Region | Strategic Rationale / Why Now
Government | National Energy Ministry / Agency | Ministry of Economic Affairs & Climate (NL) | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Federal Ministry for Economic Affairs and Climate Action (BMWK) | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | ADEME (France) | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Italian Ministry of Environment and Energy Security | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Spanish Ministry for Ecological Transition (MITECO) | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Danish Energy Agency | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Swedish Energy Agency | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Finnish Ministry of Economic Affairs | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Polish Ministry of Climate | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Portuguese Directorate-General for Energy and Geology (DGEG) | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Chilean Ministry of Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Peruvian Ministry of Energy and Mines | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Mexican Ministry of Energy (SENER) | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Colombian Ministry of Mines and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Argentinian Secretariat of Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Brazilian Ministry of Mines and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Uruguayan Ministry of Industry and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Costa Rican Ministry of Environment and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Panamanian Secretariat of Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Dominican Republic Ministry of Energy and Mines | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Bolivian Ministry of Hydrocarbons and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Ecuador Ministry of Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Paraguay Ministry of Public Works and Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Guatemalan Ministry of Energy and Mines | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Honduran Secretariat of Energy | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | El Salvador Ministry of Economy (Geothermal) | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Nicaraguan Ministry of Energy and Mines | LATAM | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Iceland National Energy Authority | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Turkish Ministry of Energy and Natural Resources | EU | Policy-driven urgency for heat transition and energy security
Government | National Energy Ministry / Agency | Greek Ministry of Environment and Energy | EU | Policy-driven urgency for heat transition and energy security
Government | Regional / Municipal Authority | Province of Zuid-Holland | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Province of Noord-Brabant | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Île-de-France | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Nouvelle-Aquitaine | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | State of Bavaria Energy Office | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | State of North Rhine-Westphalia | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Lombardy Energy Authority | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Tuscany | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Andalusia Energy Agency | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Region Catalonia ICAEN | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Munich – District Heating | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Paris – Climate Office | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Copenhagen – Heat Planning | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Amsterdam – Energy Transition | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Rotterdam – Heat Networks | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Vienna – Energy Planning | EU | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | Metropolitan Santiago – Energy Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Bogotá – Climate Secretariat | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Medellín – Energy & Utilities | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Mexico – Energy Secretariat | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of São Paulo – Climate Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Rio de Janeiro – Energy Planning | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Buenos Aires – Energy Transition | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Montevideo – Climate Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Lima – Energy Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Quito – Sustainability Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of San José (CR) – Energy | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of San Salvador – Energy Planning | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of Managua – Energy | LATAM | Heat-planning and regional feasibility under political timelines
Government | Regional / Municipal Authority | City of La Paz – Energy Office | LATAM | Heat-planning and regional feasibility under political timelines
Government | Public Energy / Geological Agency | IEA Geothermal Program | Global | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | IRENA | Global | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | JRC – EU Commission Energy | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | DG ENER – European Commission | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | EU Innovation Fund | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | EU LIFE Programme | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Netherlands (TNO) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | BGR – German Geological Survey | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | BRGM – French Geological Survey | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | CGS – Chilean Geological Survey | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | INGEMMET – Peru Geological Survey | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | SERNAGEOMIN – Chile | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Servicio Geológico Colombiano | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | CPRM – Brazilian Geological Survey | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Instituto Geológico Minero Argentino | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Instituto Geofísico del Perú | LATAM | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Denmark and Greenland (GEUS) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | British Geological Survey (BGS) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Spain (IGME) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Italy (ISPRA) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Sweden (SGU) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Finland (GTK) | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Iceland | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Portugal | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Austria | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Norway | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Switzerland | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Belgium | EU | Data-driven mapping and feasibility required to unlock projects
Government | Public Energy / Geological Agency | Geological Survey of Poland | EU | Data-driven mapping and feasibility required to unlock projects

## Phase2_Government
Segment | Persona | Typical Titles | Primary Concern | Trigger Words | Offer | LinkedIn Connection Template | LinkedIn Follow-up Template | Email Subject Options | Email Body Template
Government | Policy / Program Lead | Policy Officer, Program Manager, Energy Transition Lead | Meeting policy targets, budget justification, timelines | policy targets, planning, timelines, evidence-based | Free Regional Screening Brief (Policy-Aligned) | Hi {{First Name}} — noticed your role in energy transition planning at {{Organization}}. We support public bodies with fast, policy-aligned regional screening for geothermal and subsurface energy. Would be glad to connect. | Thanks for connecting. We help public agencies translate subsurface uncertainty into clear, decision-ready screening outputs that support policy and budget decisions. | Policy-aligned geothermal screening ¦ Regional energy potential insights | Hi {{First Name}}, Public energy programmes often need defensible, evidence-based insights to justify next steps and budgets. At Geotechnic Solutions, we deliver policy-aligned regional screening briefs using AI, GIS and geoscience expertise to quickly assess geothermal and subsurface energy potential. We’re offering a no-cost Regional Screening Brief to support early planning and prioritisation. Happy to share an example or discuss how this could support your current programme. Kind regards, {{Signature}}
Government | Technical / Geological Lead | Chief Geologist, Subsurface Advisor, Technical Specialist | Data quality, uncertainty framing, technical credibility | uncertainty, interpretation, data quality, defensibility | Free Regional Screening Brief (Policy-Aligned) | Hi {{First Name}} — saw your role in subsurface / geological advisory at {{Organization}}. We combine AI-supported screening with expert interpretation for early-stage regional assessments. Happy to connect. | Thanks for connecting. We support technical teams by framing subsurface uncertainty clearly in early regional screening. | Decision-ready subsurface screening ¦ Regional feasibility support | Hi {{First Name}}, We work with technical teams in public agencies who need clear, defensible subsurface interpretation early in regional energy assessments. Our policy-aligned screening briefs combine AI+GIS workflows with expert review to frame uncertainty and next steps transparently. Happy to apply this to a region you’re currently assessing. Kind regards, {{Signature}}
Government | Procurement / Project Lead | Procurement Officer, Project Manager, Programme Coordinator | Scoping studies, procurement readiness, cost control | scope, procurement, readiness, cost-effective | Free Regional Screening Brief (Policy-Aligned) | Hi {{First Name}} — noticed your work on energy project procurement at {{Organization}}. We help public bodies scope early feasibility clearly before tendering. Would be glad to connect. | Thanks for connecting. We support procurement and project teams with early screening that clarifies scope and reduces downstream study costs. | Reducing risk before procurement ¦ Early regional screening | Hi {{First Name}}, Before commissioning full studies, public bodies often need a clear, cost-effective view of regional energy potential. We provide early regional screening briefs that help define scope, priorities and uncertainty before procurement. Happy to discuss whether this could support an upcoming project. Kind regards, {{Signature}}

## Phase2_Developers
Segment | Persona | Typical Titles | Primary Concern | Trigger Words | Offer | LinkedIn Connection Template | LinkedIn Follow-up Template | Email Subject Options | Email Body Template
Developer | Head of Development / Project Director | Head of Development, Project Director, Development Manager | Go/no-go decisions, site viability, timelines | feasibility, site screening, go/no-go, constraints | Free Desktop Feasibility Snapshot | Hi {{First Name}} — noticed your work on project development at {{Company Name}}. We support developers with fast desktop feasibility screening to clarify site viability early. Would be glad to connect. | Thanks for connecting. We help developers get early feasibility signals on geothermal and renewable sites to support go/no-go decisions. | Early feasibility signal for your projects ¦ Fast site screening support | Hi {{First Name}}, Project developers often face uncertainty early around site viability and subsurface constraints. At Geotechnic Solutions, we provide fast desktop feasibility snapshots using AI, GIS and geoscience expertise to help teams decide where to focus — and where not to. We’re offering a no-cost Desktop Feasibility Snapshot to support early decisions. Happy to share an example or discuss one of your sites. Best regards, {{Signature}}
Developer | Subsurface / Technical Lead | Geothermal Lead, Subsurface Manager, Technical Director | Data quality, uncertainty, technical defensibility | uncertainty, interpretation, constraints, data quality | Free Desktop Feasibility Snapshot | Hi {{First Name}} — saw your role in subsurface / technical development at {{Company Name}}. We combine AI and expert interpretation to support early feasibility screening. Happy to connect. | Thanks for connecting. We help technical teams frame uncertainty clearly in early-stage feasibility. | Decision-ready subsurface insights ¦ Early technical screening support | Hi {{First Name}}, We work with technical teams who need clear, defensible subsurface interpretation early in project development. Our desktop feasibility snapshots combine AI-supported screening with expert review to frame uncertainty and next steps clearly. Happy to apply this to a current site if helpful. Best regards, {{Signature}}
Developer | Commercial / BD Lead | Business Development, Commercial Manager | Project value, pipeline growth | pipeline, scalability, value, speed | Free Desktop Feasibility Snapshot | Hi {{First Name}} — noticed your focus on project pipeline growth at {{Company Name}}. We help developers screen sites quickly to scale pipelines efficiently. Would be glad to connect. | Thanks for connecting. We support teams scaling project pipelines through fast feasibility screening. | Scaling your project pipeline faster ¦ Early feasibility support | Hi {{First Name}}, Scaling a development pipeline requires fast, reliable site screening. We help developers identify promising geothermal and renewable sites early through AI+GIS-supported desktop feasibility snapshots. Happy to explore how this could support your pipeline. Best regards, {{Signature}}

## Phase2_Investors
Segment | Persona | Typical Titles | Primary Concern | Trigger Words | Offer | LinkedIn Connection Template | LinkedIn Follow-up Template | Email Subject Options | Email Body Template
Investor | Partner / Principal | Partner, Managing Partner, Principal, Investment Director | Capital allocation, IC defensibility, risk vs upside | de-risk, early signal, screening, capital efficiency, no-go | Free Investment De-Risk Scan | Hi {{First Name}} — I noticed {{fund focus / recent deal}}. We support climate & infra investors with fast, AI-supported subsurface screening to de-risk projects early. Would be glad to connect. | Thanks for connecting, {{First Name}}. We help investors get early go/no-go signals on geothermal or subsurface-heavy opportunities through fast desktop scans. Happy to share an example or run a short no-cost de-risk scan. | Quick de-risking insight for geothermal investments ¦ Early screening for subsurface-heavy deals ¦ Fast feasibility signal for climate investments | Hi {{First Name}}, {{Fund Name}} is active in climate & infrastructure, where subsurface uncertainty often sits upstream of investment risk. At Geotechnic Solutions, we combine AI, GIS and geoscience expertise to deliver fast desktop scans for geothermal and critical-mineral opportunities. These help teams decide whether a project is worth deeper diligence — or not. We’re offering a short, no-cost Investment De-Risk Scan to sanity-check potential sites or regions. Happy to walk you through an example if useful. Best regards, {{Signature}}
Investor | Platform / ESG Lead | Platform Director, Head of Value Creation, ESG Director | Portfolio support, ESG defensibility, standardisation | standardised, decision-ready, portfolio-wide, repeatable | Free Investment De-Risk Scan | Hi {{First Name}} — noticed your work on portfolio value creation at {{Fund Name}}. We support climate investors with standardised, decision-ready subsurface screening. Would be glad to connect. | Thanks for connecting. We help funds standardise early geothermal and subsurface screening across portfolios to support investment teams and ESG reporting. | Standardised screening for climate portfolios ¦ Decision-ready geothermal insights | Hi {{First Name}}, We work with climate investors looking to standardise early-stage geothermal and subsurface screening across portfolios. Our AI+GIS-supported scans provide decision-ready outputs that investment and ESG teams can reuse consistently. Happy to share an example or discuss where this could support your platform efforts. Best regards, {{Signature}}
Investor | Investment Manager / Associate | Investment Manager, Senior Associate, Analyst | Fast diligence, red-flag identification | quick scan, sanity check, red flags, early insight | Free Investment De-Risk Scan | Hi {{First Name}} — saw your focus on climate investments at {{Fund Name}}. We help teams get quick subsurface sanity checks before deep diligence. Would be glad to connect. | Thanks for connecting. We support investment teams with quick scans to flag risks and support IC memos early. | Quick subsurface sanity check ¦ Early diligence support for climate deals | Hi {{First Name}}, We support investment teams who need fast subsurface insights to support early diligence and IC preparation. Our desktop scans highlight red flags and potential upside early, before time and budget are committed. Happy to apply this to a current opportunity if useful. Best regards, {{Signature}}

## Phase 3 Execution System
Section | Rule / Step | Guideline | Details / Notes
Outreach Cadence | Weekly Volume | 20–30 new outreaches per week | Investors ~10, Developers ~10, Government ~5–10
Outreach Cadence | Daily Routine | 5 new outreaches per day | 30–45 minutes total
Channel Rules | Day 1 Rule | Use one channel only | LinkedIn OR Email, not both
Channel Rules | Default Channel | LinkedIn first | Unless strong email confidence (gov/dev banks)
Follow-up | Follow-up #1 | Send after 5–7 business days | Value nudge, example or insight
Follow-up | Follow-up #2 | Send after 10–14 business days | Clean exit, stop after
Qualification | Green Flags | Prioritize active needs | Looking at sites, need assessment, next steps
Qualification | Yellow Flags | Clarify timing | Curious, send info, later this year
Qualification | Red Flags | Park politely | Fishing for free work, no decision power
Calls | Call Length | 15–30 minutes max | Do not exceed
Calls | Agenda Step 1 | Context | What decision are they trying to make?
Calls | Agenda Step 2 | Uncertainty | What is unknown or risky?
Calls | Agenda Step 3 | Fit Check | Is this early-stage screening?
Calls | Agenda Step 4 | Next Step | Free scan or paid follow-up
Conversion Path | Step 1 | Outreach → Conversation | Initial engagement
Conversion Path | Step 2 | Free Scan | Clearly scoped, fast
Conversion Path | Step 3 | Delivery | Maps + recommendation
Conversion Path | Step 4 | Paid Follow-up | Pre-feasibility or deeper study
Metrics | Track Weekly | Outreach, Replies, Calls, Scans, Paid Work | Ignore vanity metrics
Metrics | Healthy Benchmarks | 10–20% reply, 3–5% calls | Early-stage reference
AI Agent | Preparation | Prepare daily outreach batches | Segment-aware
AI Agent | Drafting | Draft messages & follow-ups | No strategy changes
AI Agent | Monitoring | Flag stalled leads & patterns | Suggest prioritisation
AI Agent | Governance | Do NOT change offers or segments | Human approval required

## Templates
Segment | Subject Template | Email Body Template (edit freely) | LinkedIn DM Template (edit freely) | Default Offer | CTA
Investors & Finance | De-risk geothermal / critical minerals diligence in weeks | Hi {FirstName}, I’m {Sender} from Geotechnic Solutions. We combine AI, GIS and geoscience to quickly screen geothermal and critical-mineral opportunities and produce decision-ready maps + risk framing. If useful, I can share a sample 5–10 page screening report and how investors use it as an early diligence input. Open to a 15‑minute intro next week? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — quick one: we help investors de‑risk geothermal + critical mineral deals with fast AI+GIS screening reports. Worth a 15‑min intro? | Sample screening report | Book 15-min call / reply ‘yes’
Land Owners & Developers | What’s the best energy use of your land? (fast screening) | Hi {FirstName}, We help landowners and developers quickly screen whether a site is better suited for geothermal heat, wind/solar, or ‘not worth it yet’ — using AI+GIS and public datasets. If you share a polygon/site boundary, we can return a concise map pack + recommended next steps. Want to try a quick scan? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — we can screen your site (polygon) for geothermal + wind/solar potential and return a decision-ready map pack. Interested? | Free quick scan | Send polygon / book call
Government & Public Agencies | Rapid regional screening for geothermal / critical minerals | Hi {FirstName}, Geotechnic Solutions supports municipalities and agencies with rapid desktop screening: geothermal play concepts (temperature at depth) and critical-mineral prospectivity summaries. Deliverables are board/decision-ready maps + clear uncertainty framing, so you only fund deeper studies where needed. Would it help to see an example output for a comparable region? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — we deliver rapid, decision-ready geothermal / critical mineral screening maps for regions, with clear uncertainty framing. Want an example output? | Example regional map pack | Reply for sample / schedule
Renewable Energy Companies | Shortlist sites faster: AI+GIS pre‑feasibility (wind/solar/geothermal) | Hi {FirstName}, We help developers shortlist sites faster with standardized AI+GIS desktop screening (resource context, constraints, early cost ranges, and next steps). If you have multiple candidate sites, we can compare them with clear trade-offs and recommended deeper studies. Open to a quick call to see if this fits your pipeline? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — we help developers compare candidate sites fast (AI+GIS screening + clear trade-offs). Worth a quick call? | Site comparison report | Book 15-min call
Mining & Exploration | Prospectivity scans for REE / critical minerals (early target ranking) | Hi {FirstName}, We run early-stage prospectivity scans for REE and critical minerals: regional briefs + prospectivity maps + target ranking, plus high-level ESG/permitting flags. If you’re screening new jurisdictions or targets, we can reduce uncertainty before field spend. Would a sample prospectivity map pack be useful? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — we produce early-stage REE/critical-mineral prospectivity maps + target ranking to reduce uncertainty before field spend. Want a sample? | Sample prospectivity map | Reply for sample
Industrial Energy Users | Is geothermal heat viable at your site? (fast desktop screening) | Hi {FirstName}, We quickly assess whether a facility/site could support geothermal heat (temperature-at-depth context, conceptual reservoir view, and early cost ranges) — so you can decide if deeper work is worth it. If you share the site location/boundary and your heat needs, we can return a concise feasibility note. Open to a short call? Best, {Sender} Geotechnic Solutions | Hi {FirstName} — we can quickly screen if geothermal heat is viable at your site and return a concise feasibility note. Interested? | Concise feasibility note | Book 15-min call

## LEAD_INTAKE (READ-ONLY FOR AGEN
Name | Organization | Title | Segment and sub-segment | Region | Priority | Why relevant now | Source | LinkedIn (Sales Navigator) URL | date entered
Andy Wood | Primeval Energy Ltd | Chief Executive Officer | Developer – Geothermal energy developer | Rustington, England, UK | P1 | CEO of Primeval Energy and geothermal champion advocating for geothermal energy projects in Europe. | Sales Navigator search – geothermal Europe | https://www.linkedin.com/sales/lead/ACwAAAAfWIBNTr9yIns-Gqu4ZxiIHVfR5rvzANA | 2026-01-06
Andrew Chukwuenweniwe | Fidan Capital Management Limited | Managing Director | Investor – Infrastructure & renewable energy financing | London, United Kingdom | P1 | Global capital‑raising specialist focusing on infrastructure and renewable energy projects; potential investor for geothermal and critical minerals. | Sales Navigator search – geothermal investor Europe | https://www.linkedin.com/sales/lead/ACwAAACpxL8BTiZUv0ZeGb-2Z9AgtxReK5Vy0cQ | 2026-01-06
Frank Drennan | WSP | Service Line Director – Energy Transition & Low Carbon | Developer/Consultant – Engineering firm | Send, England, UK | P1 | Leads energy transition and low‑carbon services at WSP, supporting renewable and geothermal projects. | Sales Navigator search – geothermal energy director Europe | https://www.linkedin.com/sales/lead/ACwAAAC9H50BVLYkXf9s9Pi0czw91kYmkq5wa8E | 2026-01-06
Greg Jackson | Octopus Energy | Founder & Chief Executive Officer | Developer – Renewable energy utility | London, United Kingdom | P1 | CEO of a leading renewable energy company expanding into geothermal and innovative energy solutions. | Sales Navigator search – geothermal investor Europe | https://www.linkedin.com/sales/lead/ACwAAAB2FbIBlESjdOb4BoXJwE9o96vZK1oOym8 | 2026-01-06
Axel A. O. Wenke | Neptune Energy Innovations GmbH | Director New Energy Business Development | Developer – Energy innovation & new energy | Berlin, Germany | P2 | Leads new energy business development focusing on renewable and geothermal technologies in Europe. | Sales Navigator search – geothermal Europe | https://www.linkedin.com/sales/lead/ACwAAAGrRlkBSxDfUq4lzQGu2IJZa8tYBFeVpt0 | 2026-01-06
Alexander Richter | Rafal / ThinkGeoEnergy | Board Member / Founder | Thought leader & Advisor – Geothermal industry intelligence | Reykjavík, Iceland | P1 | Geothermal thought leader and founder of ThinkGeoEnergy providing market intelligence and advisory for geothermal and critical minerals projects. | Sales Navigator search – geothermal government Europe | https://www.linkedin.com/sales/lead/ACwAAAAfWIBNTr9yIns-Gqu4ZxiIHVfR5rvzANA | 2026-01-06
Greg Krupa | Artisan Tropic | Partner & Head of Investor Relations | Investor – Climate and deep‑tech ventures | Quito, Pichincha, Ecuador | P2 | Serial impact entrepreneur and climate investor engaged in regenerative agriculture, deep tech and renewable energy ventures across LATAM. | Sales Navigator search – geothermal Latin America investor | https://www.linkedin.com/sales/lead/ACwAAAFHu2gBLb3aJ2NOgQSXMNyHtzJuoeArbfw | 2026-01-06
Roberto Alhucema | Enel Green Power / Enel Group (Chile) | Head of Wind, Thermal & Geothermal Generation Chile | Developer – Utility company | Santiago, Chile | P1 | Oversees wind, geothermal and thermal generation for Enel in Chile, making decisions on new renewable projects. | Sales Navigator search – geothermal Chile (Latin America) | https://www.linkedin.com/sales/lead/ACwAAAGvWzIBL0m8K3ZHViDTzfa2k2LxxYpazxc | 2026-01-06
Rüdiger Trenkle | Geotermia Chile Ltda. / SolarLatam | Business Leader / CEO / Consultant | Developer & Consultant – Renewable energies & PPP infrastructure | Santiago, Chile | P2 | Experienced CEO and consultant leading Geotermia Chile and SolarLatam, involved in geothermal and solar development projects. | Sales Navigator search – geothermal Chile | https://www.linkedin.com/sales/lead/ACwAAAHIkzoBcSwS1s8Y-LjeHfKgY8pTWcPepo0 | 2026-01-06
Sandro Bruni | ENGIE Chile | Business Development Manager | Developer – Renewable energy utility | Santiago, Chile | P2 | Drives business development for ENGIE Chile, including geothermal and renewable projects. | Sales Navigator search – geothermal Chile | https://www.linkedin.com/sales/lead/ACwAAAHGEEoBxTfcYL_mIafI8i82m-OvP4n35bU | 2026-01-06
Cozmo Kampanaos | Aphaia Advisory | Director – Mining Strategy, Operations & Advisory | Consultant – Critical minerals and mining strategy | Seer Green, England, UK | P2 | Provides feasibility, due diligence and financing strategies for mining and critical minerals projects across Europe. | Sales Navigator search – critical minerals Europe investor | https://www.linkedin.com/sales/lead/ACwAAAHPDSMBdz5-hkPgrgma0GVD73ggKe9Y5Ag | 2026-01-06
Elkin Javier Casas Rico | John T. Boyd Company | Consultant – Critical Minerals Value Chains Project (Brazil & LAC) | Government/Public agency consultant – Critical minerals value chains | Barcelona, Catalonia, Spain | P2 | Advises governments and companies on critical minerals value chains in Brazil and Latin America, focusing on energy transformation and public policy. | Sales Navigator search – critical minerals Europe investor | https://www.linkedin.com/sales/lead/ACwAAAGL63MB2hpGN9zBtAxQnjVgJuIR-QxY9kM | 2026-01-06
Neil Atkinson | Self‑employed | Freelance Instrumentation & Monitoring Specialist (AI advisor) | Consultant – Geotechnical instrumentation & AI‑based monitoring | Warrington, England, UK | P2 | Provides AI‑driven instrumentation and monitoring solutions for infrastructure and geotechnical projects. | Sales Navigator search – AI GIS decision support energy Europe | https://www.linkedin.com/sales/lead/ACwAAAActgIBjkXwH6_3PhmHjb--7o_f70Xphvg | 2026-01-06
Kenneth Øyen‑Eriksen | Geodata AS | Strategic Advisor (Strategisk rådgiver) | Vendor – GIS and decision‑support solutions | Oslo, Norway | P2 | Seasoned GIS professional at Geodata AS, providing geospatial analytics and decision‑support services for energy and infrastructure projects. | Sales Navigator search – AI GIS decision support energy Europe | https://www.linkedin.com/sales/lead/ACwAAAGg_SYBOQ2yK8eS9lJcZz9_oG7CHzUuAlw | 2026-01-06
Anna Reichstein | Bundesanstalt für Geowissenschaften und Rohstoffe (BGR) | Wissenschaftliche Mitarbeiterin (Scientific Researcher) – Data Scientist, Remote Sensing & Geospatial Analytics | Government/Public agency – Geoscience & critical raw materials research | Hannover, Germany | P1 | Data scientist using remote sensing and geospatial analytics to support Europe’s critical raw materials supply and resource assessment. | Sales Navigator search – AI GIS decision support energy Europe | https://www.linkedin.com/sales/lead/ACwAAAGjCGQBjCb6H1gjZv6kQ5XG0dYCCzYHjDI | 2026-01-06
Branislav Todorovic | Self‑employed | Project Management & Research (Environment, Water & Energy, ICT) | Consultant – Environmental & energy project management | Athens, Greece | P2 | Veteran senior engineer and project manager with 30+ years’ experience in environment, water and energy projects, now advising as independent consultant. | Sales Navigator search – AI GIS decision support energy Europe | https://www.linkedin.com/sales/lead/ACwAAAGtrR0BOsHhM3XDs7j4nKrivkCpXzC2rWY | 2026-01-06
Tijana Š. | NCR Voygix | Incident Management Analyst ¦ GIS Analyst | Vendor/Analyst – Geospatial data & incident management | Belgrade, Serbia | P2 | Specializes in using geospatial data and GIS analysis for strategic decision‑making and incident management. | Sales Navigator search – AI GIS decision support energy Europe | https://www.linkedin.com/sales/lead/ACwAAAGqquABYgHwbL5Cg1n89Dm5c7riXWu8LcM | 2026-01-06

## PROMOTE_TO_OUTREACH_QUEUE
Step | Check | Requirement | Action if NO | Notes | Promote Approved (YES/NO)
1 | Source confirmed | Lead from LEAD_INTAKE / Sales Navigator / trusted source | Do not promote | Include source URL
1 | No prior outreach | No email or LinkedIn sent before | Do not promote | Check history manually
2 | First name present | First_Name filled | Complete before promoting | Required
2 | Last name present | Last_Name filled | Complete before promoting | Required
2 | Organization present | Organization filled | Complete before promoting | Required
2 | Role/title present | Current role/title filled | Complete before promoting | Use LinkedIn headline
2 | Region present | Country or city+country filled | Complete before promoting | No guessing
3 | Segment selected | Segment = Investors / Developers / Government & Public Agencies | Fix segment | ENUM only
3 | Sub-segment valid | Sub-segment matches segment logic | Fix sub-segment | No free-text drift
3 | Persona derived | Persona derived strictly from title | Fix persona | Never infer
4 | Offer matches segment | Offer matches locked offer exactly | Fix offer | No variants allowed
5 | Priority set | Priority = P1 or P2 | Set priority | P1 preferred
5 | Status set | Status = Not contacted | Fix status | No blanks allowed
6 | Channel available | LinkedIn URL OR Email present | Add channel | One is enough
6 | Channel selected | Channel = LinkedIn OR Email | Fix channel | Day‑1 rule
7 | Row created | Lead copied to OUTREACH_QUEUE | Create row | New Lead_ID
7 | Lead_ID unique | Lead_ID not used before | Fix ID | Increment only
7 | Notes updated | Notes include promotion date | Add note | Audit trail
7 | Agent_Ready flag | Agent_Ready = FALSE | Fix flag | Set TRUE after review
8 | Final sanity check | You would send this today | Do not promote | Human gate
8 | Timing appropriate | Lead relevant now | Park or downgrade | Use P2 if unsure

## OUTREACH_QUEUE
Lead_ID | First_Name | Last_Name | Organization | Title | Segment | Sub_Segment | Persona | Region | LinkedIn_URL | Email | Priority | Status | Channel | Offer | First_Outreach_Date | FU1_Due_Date | FU2_Due_Date | Hook_Seed | Notes | Last_Updated | Agent_Ready
1 |  |  |  |  | Investors | [5 empty] | P1 | Contacted |  | Free Investment De-Risk Scan |  |  |  |  | PLACEHOLDER P1 investor slot — fill Name/Org/Title/Region/LinkedIn or Email before drafting. |  | FALSE
2 |  |  |  |  | Investors | [5 empty] | P1 | Not contacted |  | Free Investment De-Risk Scan |  |  |  |  | PLACEHOLDER P1 investor slot — fill Name/Org/Title/Region/LinkedIn or Email before drafting. |  | FALSE
3 |  |  |  |  | Investors | [5 empty] | P1 | Not contacted |  | Free Investment De-Risk Scan |  |  |  |  | PLACEHOLDER P1 investor slot — fill Name/Org/Title/Region/LinkedIn or Email before drafting. |  | FALSE
4 |  |  |  |  | Investors | [5 empty] | P1 | Not contacted |  | Free Investment De-Risk Scan |  |  |  |  | PLACEHOLDER P1 investor slot — fill Name/Org/Title/Region/LinkedIn or Email before drafting. |  | FALSE
5 |  |  |  |  | Investors | [5 empty] | P1 | Not contacted |  | Free Investment De-Risk Scan |  |  |  |  | PLACEHOLDER P1 investor slot — fill Name/Org/Title/Region/LinkedIn or Email before drafting. |  | FALSE
6 | Andrew | Chukwuenweniwe | Fidan Capital Management Limited | Managing Director | Investors | Infrastructure & renewable energy financing | Partner / Principal | London, United Kingdom | https://www.linkedin.com/sales/lead/ACwAAACpxL8BTiZUv0ZeGb-2Z9AgtxReK5Vy0cQ |  | P1 | Not contacted | LinkedIn | Free Investment De-Risk Scan |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE
7 | Andy | Wood | Primeval Energy Ltd | Chief Executive Officer | Developers | Geothermal energy developer | Head of Development / Project Director | Rustington, England, UK | https://www.linkedin.com/sales/lead/ACwAAAAfWIBNTr9yIns-Gqu4ZxiIHVfR5rvzANA |  | P1 | Not contacted | LinkedIn | Free Desktop Feasibility Snapshot |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE
8 | Frank | Drennan | WSP | Service Line Director – Energy Transition & Low Carbon | Developers | Engineering / advisory (energy transition) | Commercial / BD Lead | Send, England, UK | https://www.linkedin.com/sales/lead/ACwAAAC9H50BVLYkXf9s9Pi0czw91kYmkq5wa8E |  | P1 | Contacted | LinkedIn | Free Desktop Feasibility Snapshot |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE
9 | Greg | Jackson | Octopus Energy | Founder & Chief Executive Officer | Developers | Renewable energy utility | Head of Development / Project Director | London, United Kingdom | https://www.linkedin.com/sales/lead/ACwAAAB2FbIBlESjdOb4BoXJwE9o96vZK1oOym8 |  | P1 | Not contacted | LinkedIn | Free Desktop Feasibility Snapshot |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE
10 | Roberto | Alhucema | Enel Green Power / Enel Group (Chile) | Head of Wind, Thermal & Geothermal Generation Chile | Developers | Utility (wind/thermal/geothermal) | Head of Development / Project Director | Santiago, Chile | https://www.linkedin.com/sales/lead/ACwAAAGvWzIBL0m8K3ZHViDTzfa2k2LxxYpazxc |  | P1 | Not contacted | LinkedIn | Free Desktop Feasibility Snapshot |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE
11 | Anna | Reichstein | Bundesanstalt für Geowissenschaften und Rohstoffe (BGR) | Scientific Researcher – Data Scientist, Remote Sensing & Geospatial Analytics | Government & Public Agencies | Public energy / geological agency | Technical / Geological Lead | Hannover, Germany | https://www.linkedin.com/sales/lead/ACwAAAGjCGQBjCb6H1gjZv6kQ5XG0dYCCzYHjDI |  | P1 | Not contacted | LinkedIn | Free Regional Screening Brief (Policy-Aligned) |  |  |  |  | Promoted from LEAD_INTAKE (Sales Navigator). |  | FALSE